ANNEX II: TERMS OF REFERENCE                                                                   REF No. TD01_PP3_BGMK0300064

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

Center for Development of Third-Northeast Planning Region Kumanovo

## Country background

The Beneficiary Country is a landlocked country on the Balkan Peninsula with an area of 25,713 km2 and population of 2,022,547 inhabitants (source: Census 2002), living in 84 municipalities.  It shares a border with Greece to the south, Bulgaria to the east, Serbia and Kosovo to the north, and Albania to the west. It has a diverse topography with high mountains and deep valleys, large and small natural lakes and picturesque rivers. The agricultural land covers 50% of the surface area while forests cover about one third from the country. The country has a diverse climate, with eight climatic regions.

The geographic location places the country at the crossroads of South-Eastern Europe, making it an important transit route for land traffic between Central Europe, the Aegean Sea, the Black Sea and the Adriatic Sea.

The country is 80% mountainous, rising to its highest point at Mountain Korab (peak 2,764 meters) with the lowest elevation (44 m) on the Vardar River at the border with Greece. Three climatic types overlap in the country: Mediterranean, moderately continental and mountainous, producing hot, dry summers and cold, snowy winters.

The hydrographical territory belongs to the following river basins: the Vardar river basin which gravitates towards the Aegean Sea, the Crn Drim river basin, comprising the Prespa and Ohrid lake basins, gravitates to the Adriatic Sea and the Strumica river basin gravitates to the Aegean Sea. A negligible part of the hydrographical territory drains to Danube river basin. There are three major natural lakes: Ohrid, Prespa and Dojran lakes

## Current situation in the sector

Over the period since achieving its independence, the Beneficiary Country has been striving to build a stable political and economic community, with a legal system able to facilitate rapid integration into the European Union and the wider international community. This primary strategic goal has given rise to sectoral targets, one of which is the establishment of efficient environmental protection measures in order to provide a basis for an improved quality of life.

The problems and challenges facing the development of green infrastructure, affect various sectors and spheres of public development and the quality of life of citizens, which necessitates the application of integrated, complex, complementary approaches for solving them, which at the same time provide an opportunity for individual and local initiatives.

The development of green infrastructure will connect existing natural areas and support the maintenance of healthy, functioning and sustainable urban ecosystems, thus contributing to the improvement of the quality of the urban environment. The construction of quality green infrastructure can only be achieved through an integrated approach to the development of the urban environment and its spatial planning.

The national legislation that deals with the issues of urban green spaces and green infrastructure is dealt with in the following laws: the Law on Urban Greenery (Official Gazette of the Republic of Macedonia, No. 11/2018), the Law on Urban Planning (Official Gazette of the RSM, No. 32/ 2020), as well as their by-laws (regulations), the Law on communal activities ("Official Gazette of RSM" no. 302/20), the Law on building ("Official Gazette of RSM" no. 130/09, no. 111/ 23), the Law on Nature Protection ("Official Gazette of RSM" No. 67/04, 14/06, 84/07, 35/10, 47/11, 148/11, 59/12, 13/13, 163/13 , 41/14, 146/15, 39/16, 63/16, 113/18 and 151/21) the Law on Local Self-Government ("Official Gazette of RM" No. 5/2002), the Law on Public Enterprises, and the Law for the city of Skopje ("Official Gazette of the Republic of RM " No. 55/04 and 158/11) and the Expropriation Law ("Official Gazette of the Republic of RM " "Official Gazette of the Republic of RNM " No. 95/2012; 131/2012; 24/2013 27/2015; 192/2016; 111/2023.

The law on urban greenery, adopted in 2018, perceives the issues related to urban greenery in the most comprehensive way. Other laws address different aspects of urban green spaces. Thus, the Law on Urban Planning deals with the planning of land/space intended for greenery, the Law on Construction only with certain aspects of construction/creation of green spaces, and the Law on Communal Activities with the way of raising, maintaining and reconstructing green areas. Therefore, in the following, the basic legal solutions related to urban green areas will be presented.

It should be noted that in the past several attempts were made by various professional groups to pass a special law, which will apply exclusively to green areas (in cities, settlements, recreational areas), but unfortunately these attempts in the eighties and nineties years of the last century did not end with a comprehensive and functional law and by-laws that would regulate this area.

· Law on Urban Greenery

The Law on Greenery, adopted in 2016, is the first legal document that regulates numerous issues related to public green areas, from their planning to their maintenance, in an appropriate legal form. In 2018, the Law on Greenery was replaced by a new one - the Law on Urban Greenery (Annex 2). This Law regulates a number of aspects relevant to urban greenery, aiming to manage urban greenery in a way that will permanently preserve and increase its values. The Law regulates a number of aspects, from planning and defining standards and norms for planning and maintenance to establishing a system for managing and financing urban greenery. The law covers green areas within the planning scope of urban plans and other urban planning documentation, as well as green areas in the immediate surroundings of the city that are used as recreational or protective/protected areas.

Urban planning law

The Law systematically and hierarchically regulates urban planning and defines the organization, purpose, form and manner of use of space and land, as well as the spatial and functional conditions for the construction and use of the planned buildings. According to this, the land intended for greenery of different types is also determined. By this Law, urban greenery, i.e., urban green areas, are defined as "unbuilt construction land" and it is established that "unparcelled construction land is construction land on which no construction plots have been formed, land that is limited by regulatory lines and that serves for general use, that is, for the construction of public spaces: streets, squares, infrastructures, urban greenery, etc.

From the perspective of the development of green infrastructure in urban areas, several strategic documents have been prepared in the Republic of North Macedonia so far at the local level, in which green infrastructure and its application in planning the development of cities is listed as one of the key activities for reducing pollution in the cities themselves. Unfortunately, the development of green infrastructure is at a very low level and it can be said that still green infrastructure as a tool for creating green cities is not recognized by planners and other stakeholders for urban development.

## Related programmes and other donor activities

A number of donors have supported environment sector in relation with the reduction of air pollution, climate change resilience and urban greening including the EU, USAID, World Bank Group, the Swiss Agency for Development and Cooperation and the UNDP.

# OBJECTIVES & EXPECTED OUTPUTS

## Overall objective

The overall objective (Impact) to which this action contributes is:

Achieving a sustainable functional connection of the natural and planned elements of the green system in the urbanized cross-border environment Kyustendil - Kumanovo, so that the functioning of the green infrastructure provides multiple benefits for people and continuously improves the quality of life while preserving and development of the natural environment

## Specific objective(s)

The specific objectives of this contract are as follows:

- Providing specified expertise in the area of environment and green infrastructure;

- Providing adequate visibility of the project;

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

LOT 1 – Consultancy

- Elaboration of Green strategy

- Elaboration of Action plan

- Organization of training (40 participants) and providing of trainers (developed trainings curriculum, presentation and working materials, reports) for one two days trainings

LOT 2- Communication and visibility materials

- Development of Communication plan

- Creation of CBC network and design of website

- Design and printing of Project information material

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- There are available experts for formulation of strategic documents.

- There are relevant persons interested to participate on the training

- Sufficient flow of relevant information for the project implementation between the involved parties

## Risks

- Lack of sufficient information/data and delays in ensuring available documents, necessary for the implementation of the contract

# SCOPE OF THE WORK

## General

### Description of the assignment

LOT 1 Consultancy

The contract should support the Centar for development of Third North East Planning region in successfully implementation of the project through development of Green infrastructure strategy (2025 – 2035) for North East Region, North Macedonia and Municipality of Kyustendil, Bulgaria and Action Plan (2025 – 2030) for Municipality of Kumanovo and Municipality of Kyustendil. Recognizing the large role that the green infrastructure has to play in protection of environment and  improvement of the quality of life in the urban and per-urban areas and taking in consideration that this type of infrastructure and this way of solving certain communal problems in cities is not yet applied to a sufficient extent in the North Eastern planning region of North Macedonia, Municipality of Kumanovo  and Municipality of Kustendil, within the framework of this activity a strategy and action plan for green infrastructure should be developed. Both strategic documents should be developed in cooperation with Contracting Authority and Municipality of Kyustendil. In the frame of this Lot Capacity Building Programme for green infrastructure (GI) will be implemented. One joint two days training with topic "Green infrastructure basic and utilization" should be organized in Kumanovo.

LOT 2 Communication and visibility materials

Center for development of the Third North East planning region with the aim to provide visibility of the project there is a need for design and printing of promotional and informative materials as well as printing of consumables and training materials. Also, within the scope of this project, a communication plan that will list all the procedures that should be implemented during the project in order to ensure the visibility of the project itself should be developed. On the part of the consultant, he should design and launch a project website through which a network will be created.

### Geographical area to be covered

North East Planning Region of North Macedonia and Municipality of Kyustendil Republic of Bulgaria

### Target groups

Local and regional public authorities, Local public service providers, NGO’s and other interested groups and general publics,

## Specific work

    - LOT 1 Consultancy

Activity 4.2.1.1 – Development Green infrastructure strategy (2025 – 2035) for North East Region, North Macedonia and Municipality of Kyustendil, Bulgaria

The Consultant should formulate Green infrastructure strategy (2025 – 2035) for North East Region, North Macedonia and Municipality of Kyustendil, Bulgaria. Well-designed and integrated green infrastructure increases biodiversity, supports wildlife, and enhances climate change resilience. Development of a robust GI strategy, which produces well planned and managed green infrastructure, is crucial in tackling the climate emergency.

The purpose of the Strategy is therefore to help ensure that the agenda around green infrastructure is delivered effectively in CBC areas cover with the project.

Formulation of the Strategy should include key stakeholders. In the frame of the process for development of strategy serial of four workshops should be conducted. Тhe purpose of these workshops is to ensure the participation of local and regional stakeholders in the process of formulation of the strategy and thus to gain a sense of local ownership over the formulated strategy. Workshops should include representatives of local public enterprises, representatives of their general representatives of non-governmental organizations working in the field of environmental protection, as well as representatives of the local population interested in the preparation of this strategy. The elaboration of the Strategy for the green infrastructure should consist of several main steps – analyses, reviews, proposal of the vision, targets. Consultant should set out the vision for green infrastructure in the CB region (North East planning region and Kyustendil) and to determine how future investment in green infrastructure should be provided and where investment should be targeted. The strategy should: identifies the value of green infrastructure assets and reinforces and promotes the compelling case for infesting in them; identifies existing green infrastructure assets and partnership strengths on which strategy should be build; establishes the priorities for green infrastructure priorities; sets out existing and potential mechanisms to finance green infrastructure priorities; impels planning and housing policy and other practical work to support improvement in green infrastructure across targeted areas.

Activity 4.2.1.2 - Formulation of Action Plan (2025 – 2030) for Municipality of Kumanovo and Municipality of Kyustendil

On the base of the priorities and measures formulated in the Green infrastructure strategy (2025 – 2035), Consultant should develop Action plan (2025 – 2030) for Municipality of Kumanovo and Municipality of Kyustendil. The role of the Action Plan is mainly to describe the specific steps, activities, projects, responsibilities, timeframes and financial resources for the implementation of the various activities and projects in both municipalities. The actions noted in the Action Plan should be oriented to the development of new infrastructure areas or creation of green infrastructure elements (green areas, green walls and green roofs, elements of sustainable rainwater management, planting of alleys and hedges, etc.), improvement through proposing some qualitative change – i.e. functional changes within the existing areas of green infrastructure, eliminating fragmentation and creating links, increasing the diversity of plant species etc.

Activity 4.2.1.3 – Organization of training in the frame of the capacity building programme

Capacity building will programme will begin with a series of trainings related with the green infrastructures. The main purpose of the training is to equip represents of the municipalities (departments of local economic development, urban planning and policy creation), public enterprises and other stake holders with the basic set of skills and knowledge necessary for the planning and utilization of green infrastructure. The activity will include implementation of one two-days training which should be organized in Kumanovo. The topic of the training is “Green infrastructure basic and utilization" and the training should be focused on the green infrastructure as a potential measures for solving of local and regional environmental issues.  On the training 40 represents of the invited institutions will participate (by 20 from North Macedonia and Bulgaria). The Consultant should provide three trainers with relevant background and experience and two moderators for holding the training. Also the consultant should provide adequate hall in Kumanovo to hold the training with the capacity of 40 participants, then should provide accommodation ( Half pension) for 40 participants in double rooms, lunch for 40 persons with a choice of one of three courses, dessert and salad, and includes one non-alcoholic drink per participant for each of the two days of the training, two coffee breaks for each day of the training, including coffee, tea or juice for each participant, as well as drinking water ( 2x0,5l per day and participant) in front of each participant during the training. The Consultant should develop a curriculum for the training. Trainers and moderators should prepare the needed trainings materials for the proper organization of the training, to hold the training and to prepare report. Trainings should be conducted through participatory methods, facilitation and introduction of creativity techniques. Mix of interactive and frontal activities across the day of the trainings with a core part for both the interactive and frontal session should be implemented. Possible techniques that should be used are, as it follows: interactive exercises, video materials, bottom-up methodological presentation of Case Studies from worldwide, questions and answers as well as relevant power point presentations. Method of Knowledge Café should be used to Encourage Each Person’s Contribution and to provide interaction and the exchange of ideas among participants.

For the exact date of holding of training the respective Consultant will be informed at least 30 days before the planned date of holding of training.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

4.2.2 LOT 2 Communication and visibility materials

4.2.2.1 Development of communication plan

Consultant should develop communication plan that will define the communication strategy of the project and will be used as a guide by the project partners to maximise its dissemination impact. The project communication plan should define the dissemination objectives of the project, describe the target groups of communication and dissemination activities and indicate the proper means, communication channels and materials required to reach target groups and achieve objectives. The communication strategy should include definition of aims and objectives, the identification of target groups and the overall decision about the most appropriate means, channels and resources to be deployed within a specified time-horizon. Implementation includes the planning and outlines for the communication infrastructure, activities, organisation of events and activities, monitoring and assessment of impact. Definitions of concepts and justification will be outlined for each dissemination activity.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

4.2.2.2 Creation of CBC network and website

This activity has two parts: (1) Development of website and facebook page and (2) Networking of relevant professionals, decision makers, urban planners and other relevant stakeholders in the area of the green infrastructure from the both sides of the border.  Activity includes the design and putting in operation a web-site and facebook page.

Consultant should develop website which will serve as a platform for exchanging information, ideas and good practices in the area of the green infrastructure, building contacts among main key actors and networking. Also, on the created web platform all promotional and communication materials should be presented. Project web portal should be designed, developed and implemented in 3 languages: Bulgarian, Macedonian and English. The web site should be dynamic and should have capabilities for supporting the whole range of information related with the green infrastructure. As a part of the web site on-line forum should be created which will allow participating of professionals and workers to share best practices and experiences on utilization of green infrastructure.

Consultant should present the graphic design of the website to the all Partners, who have to approve it before the development and implementation phases are undertaken. The inputs in the Facebook profile should be blog-like in nature.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

4.2.2.3 Development and printing of Project information material

The Consultant should support the Centre for Development of the Third North East Planning Region in overall process of implementation of the project trough design, printing and delivery of consumables for training and project promotional materials. Following materials and consumables should be designed, printed and delivered:

Promotional materials:

| Visibility and promotional materials | Quantity |
| --- | --- |
| banners | 2 |
| Folders | 200 |
| canvas bag | 200 |
| Hat | 200 |
| t-shirt | 200 |
| Pens | 200 |
| Notepad | 200 |
| USB | 100 |
| Promotional brochures (200) | 200 |
| leaflets (200), | 200 |
| permanent info board (10) | 5 |

Consumables:

by 40 sets of consumables for Training (one set include: folder, notebook, pen, agenda and presentations and exercise materials). Total 40 sets

Contracting Authority is obliged to present in Macedonian language the necessary texts. All aspects of preparation of materials e.g. design, colour and text translations are subject of prior approval by the Contracting Authority.

The Contractor must comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. )

## Project management

### Responsible body

The Contracting Authority for the contract is:

Center for development of the Third North East planning region

str. Ilindenska n.n., 1300 Kumanovo, North Macedonia CDNNEPR is responsible for the implementation of the project. Any issue regarding this project will be addressed to CDNEPR.

### Management structure

The Contracting Authority is Centеr for development of the Third North East planning region, Republic of North Macedonia and in that capacity, it is responsible to launch the service tender procedure, sign the service contract, authorize payments to the contractor and handle the financial management and control during project implementation. The day-to-day operational project implementation will be performed by Centеr for development of the Third North East planning region, Project office – which is responsible for implementation of project “Urban greening for healthy breathing “ financed under Bulgaria – North Macedonia IPA Cross-border Programme.

### Facilities to be provided by the contracting authority and/or other parties

The Contracting Authority will provide all available information and will fully co-operate with the Consultant/s in order to achieve the best results. Technical information and access to the existing records, any useful information and/or documentation which may be relevant to the performance of the Contract will be provided upon request.

# LOGISTICS AND TIMING

## Location

Kumanovo, East planning region of North Macedonia

## Start date & period of implementation of tasks

The intended start date is 20.12.2024 and the period of implementation of the contract will be 24 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.<

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in Macedonian in one original and two copies:

Draft final report of maximum 5 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 5 days after receipt of comments on the draft final report. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

LOT 1 Consultancy

- Developed Green Infrastructure Strategy (2025 – 2035)

- Formulated of Action plan (2025 – 2030) for green infrastructure for Kumanovo and Kyustendil

- Organized two days training

LOT 2 Communication and visibility materials

- Developed communication plan.

- Created web site and facebook page.

- Designed, Printed and delivered promotional material and training consumables.